## TestCases
Test Case Id | PreCondition | Test Scenario/Test Condition | Test Case / Test Step | Test Data | Expected Result | Remarks | Functional / Non-Functional
<Sequence number> | <Identify test scenarios> | <This cell describes what to test for i.e. the condition which is being tested for> | <This cell describes how to test i.e. the detailed testing procedure> | <Mention test data to be used> | <Describe the expected test result> | pass or Fail
TC_1 | Vendor ID | checking if the Vendor ID exist or not | Enter Vendor ID | 1001 | Vendor ID exist in the database | Pass | Functional
TC_2 | Vendor ID | checking if the Vendor ID exist or not | Enter Vendor ID | 6352652 | Vendor ID does not exist in the database | Fail | Functional
TC_3 | Add Vendor Details | entering the data with <null> | null/blank | null/blank | please the required details | Fail | Functional
TC_4 | Add Vendor Details | entering the data with required details | address details | address | address suceesfully added | Pass | Functional
TC_5 | vendor ID | entering the vendor iD | Vendor ID | blank | Vendor ID does not exist in the database | Fail
TC_6 | Vendor Type | To check if Vendor is Supplier | Enter vendor ID | 10001 | please enter the correct ID | Fail | Functional
TC_7 | Vendor Type | To check if Vendor is Supplier | Enter vendor ID | 1001 | show the result from database | Pass | Functional
TC_8

## sprint backlog
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimated Time | Adjustment Estimate | Status
1 | Drink&Delight:1 | 1 | Test Cases Template |  | 2020-08-03 | 1 hr | 2 hrs | Completed
|  | 2 | Product Backlog Sheet |  | 2020-08-03 | 1 hr | 1.5 hrs | Completed
|  | 3 | Sprint plan sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | Completed
|  | 4 | Entity Class Diagram |  | 2020-08-04 | 1.5 hrs | 2hrs | Completed
|  | 5 | Use Case Diagram |  | 2020-08-04 | 1 hr | 1hrs | Completed
|  | 6 | Sequence Diagram |  | 2020-08-04 | 1 hr | 1hrs | Completed
2 | Drink&Delight:2 | 1 | Creating a Spring boot starter project |  | 2020-08-06 | 0.5 hr | 0.5hrs | Completed
|  | 2 | Adding dependencies in Pom.xml and initializing it |  | 2020-08-06 | 1 hr | 1hrs | Completed
|  | 3 | Adding server, jpa and logging properties in application.properties |  | 2020-08-06 | 1 hr | 1hrs | Completed
3 | Drink&Delight:3 | 1 | Add Vendor Details | Dao Layer | 2020-08-07 | 3 hrs | 3hrs | Completed
|  |  |  | Service Layer | 2020-08-07 | 3 hrs | 2.5hrs | Completed
|  |  |  | Entity Layer | 2020-08-07 | 3 hrs | 3hrs | Completed
4 | Drink&Delight:4 | 1 | Edit and search vendor details | Dao Layer | 2020-08-09 | 3 hrs | 3hrs | Completed
|  |  |  | Service Layer |  | 3 hrs | 3hrs | Completed
|  |  |  | Service implemntation |  | 3 hrs | 3hrs | Completed
5 | Drink&Delight:5 | 1 | populate the data in database |  | 2020-08-10 | 3 hrs | 3hrs | Completed
|  | 2 | check data and valdiations using postman server |  | 2020-08-11 | 2 hrs | 2hrs | Completed

## product backlog
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | InventortyMGMT:001 | Design Documentation for Backend application | Mahesh | Prabhu | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 5 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | InventortyMGMT:002 | Test Plan | Mahesh | Prabhu |  | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 2hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | InventortyMGMT:003 | Bootstrapping the project | Mahesh | Prabhu | Simple | Low | RD:1 Application SetUp | RD: Drink&Delight Inventory _ver1 | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | InventortyMGMT:004 | Entity Class and TableDEsign and Populating the data | Mahesh | Prabhu | Complex | Low | RD2: Entity Class Design and RD3: Table Design | RD: Drink&Delight Inventory _ver2 | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | InventortyMGMT:005 | Dispaying the details of product | Mahesh | Prabhu | Average | Low | RD 4: Displaying the Products | RD: Drink&Delight Inventory _ver3 | Functional |  |  |  |  | 16 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
5 | 6 | Work session | High | InventortyMGMT:006 | Editing the products and Displaying the products based on product Id | Mahesh | Prabhu | Complex | Low | RD7: Displaying the products by ID and Editig The Product | RD: Drink&Delight Inventory _ver4 | Functional |  |  |  |  | 16hrs | TC_Service_02,TC_DAO_02, TC_UI_03
6 | 7 | Work session
7 | 8
8 | 9
9 | 10
10 | 11
11 | 12
12 | 13
13 | 14
14 | 15
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | InventortyMGMT:007 | Design Documentation fo Angular application | Mahesh | Prabhu | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
| 17 | Standard document | High | InventortyMGMT:008 | Test Plan | Mahesh | Prabhu
16 | 18 | Standard document |  | InventortyMGMT:009 | Design a home page having standard menus | Mahesh | Prabhu
17 | 19 |  |  | InventortyMGMT:0010 | Adding th eproduct and viewing the product and sales resport | Mahesh | Prabhu
18 | 20
19 | 21
20 | 22
21 | 23
22 | 24
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49